STRATEGIC PLAN FOR SEACOAST INTERGROUP

Draft: July 10, 2014

We have but one primary purpose—to carry this message of recovery through the Twelve Steps of Overeaters Anonymous to compulsive eaters who still suffer.

Our value to our members and our meetings is measured by our usefulness to them.

Seacoast Intergroup’s (SIG) energizing initiative is off to a great start! But we can’t think of this as a one-year plan. Don C., whose workshop gave us this initiative, also strongly recommends a long-term strategic plan so that our momentum carries forward. The following is purposefully ambitious, giving us goals to aspire to and suggesting ways to achieve them.

Why We Need a Long-Term Strategic Plan

- To maintain momentum created by Year of Abstinence

- To maintain SIG’s focus on carrying the message and supporting member’s recoveries

- To provide specific, actionable direction as new SIG officers come aboard

- To support SIG officer recruitment by helping candidates know what they will be doing

- To reduce the burden on future SIG boards for coming up with initiatives

Current Assessment

Look at all the progress we’ve already made!

Our stated goals for this energizing initiative are:

- helping members strengthen their recoveries through high-value SIG activities

- increase the number of sponsors

- improve newcomer retention

- help those in relapse

- increase opportunities to get the message out

- inspire service.

We are currently taking these actions:

- workshops

- new meeting

- new website

- 12th Step Within campaign

Imagine It Forward

So how do we take our good work forward and ensure that SIG and its meetings remain not only healthy but thriving in the future? Imagine that in 2018 we were assessing how things have gone. How will know we've accomplished our goals?

Membership and Recovery in 2018

- We have more members, and more of them stay in the rooms.

- The aggregate recovery in our area is strong and trending stronger.

- Our members are highly conversant on the Steps and how they lead to recovery.

- We have lots and lots of sponsors raising their hands at meetings.

Our Meetings in 2018

- ALL of our meetings are healthy and well attended.

- Newcomers come back.

- We have a speaker list that members want to get onto.

- Meetings routinely send 1 or 2 representatives to SIG meetings.

Support for Recovery in 2018

- We have more sponsors, including temporary sponsors, a brimming updated sponsor bank that folks want to be on, and our meetings more actively help newbies find sponsors.

- We are regularly hosting workshops and special events that draw consistently large crowds from our own IG and from others.

- Our website has a rich array of resources that members regularly use and that newbies find helpful.

Service in 2018

- Service is regularly talked about and insisted on by sponsors.

- Our IG meetings are well attended.

- Members seek offices/roles, and when people go to SIG meetings, they find that they have valuable tasks to do and want to do them.

- People want to be IG reps.

- We have standing committees for the many activities we engage in, and members want to be on them.

Public Information Activities in 2018

- We have a strong PI presence in our geographic territory.

- We have built strong connections with the medical community in our area.

- Our website draws traffic from google searches and its messaging matches our PI messaging.

Our Connection to OA as a Whole in 2018

- Our members are strongly conversant on the 12 Traditions and how they support their own recovery and OA as a whole.

- We frequently collaborate with neighboring IGs on valuable projects and have strong communication with them.

- We attend, provide valuable service to, and get great ideas from all important R6 events (as we do now) and keep our members well informed on what their 7th tradition money is doing for them.

- We do the same for WSO events.

Our Intergroup in 2018

- Members know what IG does and care about it.

- We are financially stable and contributing to R6 and WSO appropriately while funding whatever we need to do.

- We give back what Don C. and R6 have given us by becoming a resource that other IGs can turn to for experience and strength as they reenergize themselves.

If this is what we see when we imagine it forward, then we can backward plan in a broad sense from 2018 back to 2014 to find a path that can take us where we want to go.

The Road Ahead

To get to that place in 2018, we need to give our members what they have told us they need. The key themes that stood out in the survey have so far guided our decisions. They should continue to as we maintain a laser-like focus on our goals.

The following represents a possible plan of action. This is a strategic plan, not a complete tactical plan. We cannot know what the future will bring, so we plan in broad strokes now, adjust as necessary, and review our progress frequently.

2014

Year of Abstinence—which we know about already

Recruitment of next IG board—never hurts to start early!

NEAR TERM (2015–2016)

Reinforce abstinence messages from 2014: Re-offer abstinence-based workshops for newcomers and those still working toward their abstinence

2015 Year of Steps, Sponsorship, and Service: Makes sense as a follow-up to our Year of Abstinence and aligns with OA’s global strategic plan, which is Get Abstinent, Work All the Steps, Carry the Message.

Steps— Survey responders wanted more about the Steps. We have an active Big Book Step Study community in the area, but it isn’t the only approach to the Steps nor the only meeting with a Steps focus. Perhaps a series of workshops on the Steps (e.g. 1–3; 4–9; 10–12) or a weekend retreat could deepen local members’ understanding and support those who need to get beyond the first couple Steps.

Sponsorship—once members have recovery, sponsor training can be very helpful and will promote member retention—we have to give recovery away to keep it!

Service—people started showing up when we put the call out about the 2014 initiative. We know they will do service when it feels important. But we have to prove it out over time. Once we do, the message of service will resonate.

- Workshops

  - Re-offer abstinence-based half-day workshop

  - Offer sponsorship half-day workshop

  - Offer service half-day workshop?

- Develop sponsor bank

- Find best practices from meetings and other IGs for connecting sponsors and newcomers

- Encourage sponsors to suggest service to sponsees

- Monthly posts on website about

  - Sponsorship

  - Service

Member retention and reclamation—increased focus on power of fellowship to keep people and bring others back.

- Increase 12 Step Within activities?

- Newcomer orientations/workshops/events? Perhaps monthly or quarterly newcomer roundups before Thursday night 6:00 meeting?

Build more regional bridges—we have already committed to hosting Unity Day in 2015.

MID-TERM (2015–2017)

Reinforce abstinence and Steps/sponsorship/service message from previous years

  - Re-offer abstinence workshop annually

  - Offer annual sponsorship workshop if it is popular?

  - Offer condensed Steps workshop or retreat?

2016 Year of Holding On to Recovery and Staying Out of Relapse?

LONG TERM (2015–2018)

Public Information—because this can be a big undertaking and requires groups and members to coordinate with IG, this is something that we need to work carefully toward as we see a stronger sense of service.

The Traditions—our members are not well versed in them and responders didn’t consider them interesting or important. If our Intergroup thrives and grows, we will all need to learn more about and lean more heavily on the Traditions.

SIG Officer Training—Half-day workshop for SIG officers and Intergroup reps on the Traditions and Concepts. Helps service retention when future SIG officers and reps feel supported also builds local knowledge of service structure. No one has to learn on the fly. Also helps IG reps understand their role and how important they are. Perhaps see if other IGs do this or whether Region 6 can provide opportunities for this.

2018 Year of The 12 Traditions? Not sure about this because member responses were not highly positive, but we may have to reassess as we go.

RENEWAL (2018–2019)

Here we start this cycle over again by resurveying our membership, retaking our Intergroup’s inventory, and building a new plan of strategic action around these results.

Structures to Help Us Achieve Our Goals

Workshops/Events Planning

Thanks to the efforts of a few members, we are building our knowledge of how to put on a workshop or event. But we’ll need more people and a more formal means to get the work done so we don’t burn anyone out.

- Create a standing committee empowered to execute on the final strategic plan’s workshops/events.

- Draft a workshop-planning checklist/roadmap so that what we are learning now isn’t trapped in one or two people’s heads. Add it to new policies/procedures manual (see below)

- Build capacity so that we can organize as many events as we need to, spread the word effectively about them, and get enough bodies to do service at the event.

- Improve communication with surrounding Intergroups so we can cohost events, avoid duplicating their efforts, and get more interest in our workshops among their members (and vise verse).

Digital Communications Plan

Our website is evolving now, and we are trying out some great ideas. There’s plenty more out there to, and we can borrow from the websites of successful IG’s (for example WUIG group in West Chester, NY). Here are some basic things we might do:

- Create a standing committee led by a high-level service position for online communications, which includes the site plus email and any other forms of online communication we might eventually adopt. This person would be the primary blogger on the site, IG emailer, site maintainer, and email list maintainer.

- Buy our own domain name on wordpress (cheap).

- Determine how frequently our members want to see content on the site and create a practical publication schedule.

- Determine what features our members want and whether they are attainable by us.

- Determine how frequently our members want to receive email communications from IG and how many is too many.

- Support members (mostly older) who have trouble accessing online content.

- Document any important processes so that the next person in the role doesn’t have to reinvent the wheel, and add to the new policies and procedures manual (see below).

Public Information Plan

Public Information requires much coordination, persistence, people skills, and long-view thinking. It is vital to our primary purpose as an Intergroup. Our policy of attraction not promotion must also be kept always in mind.

- Create a standing committee empowered to go do what this final strategic plan recommends. Also create a high-level officer to coordinate its activities.

- Seek opportunities to carry the message via print, radio, and online forms of communication.

- Build strong connections with the area medical community, including informational mailings, one-to-ones, informational events just for the medical community, placement of information in medical offices, and any other ways we might create lasting and useful relationships.

- Consider two-hour workshops or special events that help members understand how to talk with acquaintances about OA?

- Coordinate with online communications person (above) to create a space on website just for press, medical, or other recipients of public information.

- Consider a media blitzes and/or public information nights

Development of a Policies and Procedures Manual

A one-stop shop that collects this plan and all of its suggestions for documentation, plus any other operational, role-based, or facilitation information and experience. This way future Intergroups needn’t reinvent the wheel and we can support continuity in practices across time. And because it’s not bylaws, it is easily editable and updateable.